## Master
User Story #2
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 8 | (considering we're learning Javascript + CSS)
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4 | 3
(B1) Build the city user tables according to the user's choice | 1 | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 4 | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2 | 2
(B2) Build the country user tables according to the user's choice | 1 | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 2 | 2
Button 3 (B3): create a page to display, edit, and remove saved searches | 5 | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 1 | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 1 | 1
TOTAL | 29 | 30
Sample city user table (T1)
| User input | [6 empty] | Back-end data
| User ID* | Country of choice* | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | City1 | City2 | City3 | City4 | City5
Sample country user table (T2)
| User input | [8 empty] | Back-end data
| User ID* | Country1 * | Country2* | Country3-10 | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | Currency2* | Currency3-10

## Alex
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 6
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4
(B1) Build the city user tables according to the user's choice | 1
(B1) Pull data from APIs in the backend to fill out the rest of the table | 2
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 1
(B2) Build the country user tables according to the user's choice | 1
(B2) Pull data from APIs in the backend to fill out the rest of the table | 4
Button 3 (B3): create a page to display, edit, and remove saved searches | 3
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 3
TOTAL: | 27

## Anushka
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 6
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 5
(B1) Build the city user tables according to the user's choice | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 3 (B3): create a page to display, edit, and remove saved searches | 5
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 2
TOTAL: | 32

## Andrew
Tasks to complete the story | ESTIMATE(hr):
Create a home page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 10 | (taking into consideration that we will have to learn/relearn CSS&HTML/Javascript and an SQL)
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4
(B1) Build the city user tables according to the user's choice | 3
(B1) Pull data from APIs in the backend to fill out the rest of the table | 2
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 1
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 1
Button 3 (B3): create a page to display, edit, and remove saved searches | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 3
Set up an empty database under the user's profile so any saved searches will be stored there | 2
TOTAL: | 32

## Julia
User Story #2
Tasks to complete the story | Time it takes (hr) |  | (taking into consideration that we will have to learn/relearn CSS/Javascript and SQLAlchemy)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 4
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 2
(B1) Build the city user tables according to the user's choice | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 1
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 3 (B3): create a page to display, edit, and remove saved searches | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 1
Set up an empty database under the user's profile so any saved searches will be stored there | 1
TOTAL: | 23
Sample city user table (T1)
| User input | [6 empty] | Back-end input
| User ID* | Country of choice* | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | City1 | City2 | City3 | City4 | City5
Sample country user table (T2)
| User input | [8 empty] | Back-end input
| User ID* | Country1 * | Country2* | Country3-10 | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | Currency2* | Currency3-10

## Yansong
User Story #2
Tasks to complete the story | ESTIMATE(hr):
Create a home page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches"
Button 1 (B1): create a page to display and edit preferences according to Table 1
(B1) Build the city user tables according to the user's choice
(B1) Pull data from APIs in the backend to fill out the rest of the table
Button 2 (B2): create a page to display and edit preferences according to Table 2
(B2) Build the country user tables according to the user's choice
(B2) Pull data from APIs in the backend to fill out the rest of the table
Button 3 (B3): create a page to display, edit, and remove saved searches
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly
Set up an empty database under the user's profile so any saved searches will be stored there
TOTAL: | 0